## Sheet1
OB TEAM 2 PROGRESS
Week End
|  |  | February |  |  |  | March |  |  |  |  | April
|  |  |  | 14 | 21 | 28 | 7 | 14 | 21 | 28 |  | 4 | 11 | 18 | 25
Tasks | Members |  | Week Number
| Responsible |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11 | 12
Email Local Companies | All | Estimated | Week Number 5: Completed: 3/2
Actual
Team Contract | Nadav - Expectations | Estimated | Week Number 4: Completed: 3/1
| Emily - Project Plan | Actual
Chauncey - Conclusion
Hannah - Intro
Natacha - Goals
Crystal - Procedures & Work Policy
Select Desired Company | All | Estimated | Week Number 5: Completed: 3/6
Actual
Schedule Interview Times | All | Estimated | Week Number 6: Completed: 3/16
Actual
Conduct Company Research | All | Estimated | Week Number 8: Completed: 3/20
Actual
Visit Headquarter/Store | All | Estimated | [8 empty] | Completed: 4/3 | bar: Week Number 6 to Week Number 8
Actual
Conduct Interview | Emily | Estimated | Week Number 8: Completed: 3/27
| Crystal | Actual
Chauncey
Nadav
Natacha
Hannah
Send Follow-Up Thank You Email & Summarize Interview | All | Estimated | Week Number 8: Completed: 3/27
Actual
Analysis of Interviews As Team | All | Estimated | [8 empty] | Completed: 4/3 | bar: Week Number 8
Actual
Write Paper (Including Executive Summary) | All | Estimated | [9 empty] | Completed: 4/10
Actual
Develop Presentation (Create slides/video) | All | Estimated | [9 empty] | Completed: 4/10
Actual
Memorize and Prepare Presentation | All | Estimated | [9 empty] | Completed: 4/10
Actual
Final Project Due Online | Nadav | Estimated | [10 empty] | 2015-04-13
Actual
Final Project Presentation | All | Estimated | [11 empty] | 2015-04-16
Actual
Community Service Initiative | All | Estimated | [9 empty] | Completed: 4/3 | bar: Week Number 7 to Week Number 8
Actual
Prepare CSI Presentation | All | Estimated | [11 empty] | Completed: 4/17
Actual
Memorize and Prepare CSI Presentation | All | Estimated | [11 empty] | Completed: 4/22
Actual
CSI Presentation | In Class | Estimated | [11 empty] | 2015-04-23
Actual

## Sheet1 (2)
CS411 Team Project - Team 9
Week End
|  |  |  | May |  |  |  | June |  |  |  | July
|  |  |  | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 4 | 11 | 18 | 25
Tasks | Members Responsible | Week Number
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11 | 12
Complete Google Calendar Integration | Max, Ying Hang | Estimated | 5: 2016-05-26
Actual
Add API's for customer's use | Nadav, Christine | Estimated
|  | Actual | 7: 2016-06-07
Serious debugging | All | Estimated
Actual
Get customer surveys to see what they really want | Nadav, Ying Hang | Estimated | 8: 2016-06-17
Actual
Update business needed | Max, Christine | Estimated | 8: 2016-06-17
Actual
Fault Management Testing | All | Estimated | [8 empty] | 2016-06-22 | bar: 5 to 8
Actual
Update Busness Needs | Nadav, Ying Hang | Estimated | [8 empty] | 2016-06-24 | bar: 8
Actual
Launch Alpha application | All | Estimated | [9 empty] | 2016-07-04
Actual
Launch Beta | All | Estimated | [10 empty] | 2016-07-11
Actual
Get funding for final roll out | All | Estimated | [12 empty] | 2016-07-24
Actual